## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Code explanation in Loader file | MUST HAVE | VS Code | Avinash | 3- Completed
S2 | S2 | US-001 | Code explanation in Parser file | MUST HAVE | VS Code | Avinash | 3- Completed
S3 | S3 | US-001 | Explanation of Milestone 1 document | SHOULD HAVE | Milestone 1 document | Avinash | 3- Completed
S4 | S4 | US-001 | Review of Project and Viva | MUST HAVE | VS Code | Avinash | 3- Completed
S5 | S5 | US-001 | Project review and introduction to milestone 2 | MUST HAVE | VS Code | Avinash | 3- Completed
S6 | S6 | US-001 | Code explanation of Processing file and meta data | MUST HAVE | VS Code | Avinash | 2- In Progress
S7 | S7 | US-001 | Code explanation of Processing file and main file | SHOULD HAVE | VS Code | Avinash | 3- Completed
S8 | S8 | US-001 | Review of Milestone-02 and Introduction to milestone 03 | MUST HAVE | No dependency | Avinash | 2- In Progress
S9 | S9 | US-001 | Anomaly Detection and SMTP | SHOULD HAVE | No dependency | Avinash | 3- Completed
S10 | S10 | US-001 | Standard Deviation and Z-score | SHOULD HAVE | No dependency | Avinash | 3- Completed
S11 | S11 | US-001 | Code explanation of detection file | MUST HAVE | VS Code | Avinash | 2- In Progress
S12 | S12 | US-001 | Code explanation of detection file | SHOULD HAVE | No dependency | Avinash | 2- In Progress
S13 | S13 | US-001 | Review of Project and Milestone 2 | SHOULD HAVE | No dependency | Avinash | 3- Completed
S14 | S14 | US-001 | Modification of Main file | MUST HAVE | VS Code | Avinash | 2- In Progress
S15 | S15 | US-001 | Generating random log data | MUST HAVE | VS Code | Avinash | 3- Completed
S16 | S16 | US-001 | Streamlit framework | SHOULD HAVE | No dependency | Avinash | 3- Completed
S17 | S17 | US-001 | Plotly framework | SHOULD HAVE | No dependency | Avinash | 2- In Progress
S18 | S18 | US-001 | MIT License | SHOULD HAVE | No dependency | Avinash | 3- Completed
S19 | S19 | US-001 | Project Executions | MUST HAVE | VS Code | Avinash | 2- In Progress
Note on F1: ====== ID#AAAB1JItBaU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAAB1JItBa8 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB1JItBas Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAB1JItBak Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAB1JIqqLM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB1JItBa0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB1JItBao Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB1JIqqK8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB1JIqqLQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB1JIqqLI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB1JIqqLE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB1JItBaw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB1JItBag Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB1JItBbA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB1JIqqLA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB1JItBaY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB1JItBa4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB1JItBac Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7